## Deployment Schedule
Cycle/Week | Deployment date | Retrieval date | Stream | Device ID | EMU | Position | Latitude | Longitude | Pool wrapped this week
1 | 2026-09-09 (Wed) | 2026-09-15 (Tue) | audiomoth | AM-EMU_ANCHOR_Fruit_Forest-01 | EMU_ANCHOR_Fruit_Forest | SFV-T0577 | 16.4575 | 77.9583 | No
1 | 2026-09-09 (Wed) | 2026-09-15 (Tue) | audiomoth | AM-EMU_ANCHOR_Fruit_Forest-02 | EMU_ANCHOR_Fruit_Forest | SFV-T0652 | 16.4573 | 77.9592 | No
1 | 2026-09-09 (Wed) | 2026-09-15 (Tue) | audiomoth | AM-EMU_ANCHOR_Fruit_Forest-03 | EMU_ANCHOR_Fruit_Forest | SFV-T0489 | 16.458 | 77.9569 | No
1 | 2026-09-09 (Wed) | 2026-09-15 (Tue) | audiomoth | AM-EMU_ANCHOR_Fruit_Forest-04 | EMU_ANCHOR_Fruit_Forest | SFV-T0637 | 16.4582 | 77.959 | No
1 | 2026-09-09 (Wed) | 2026-09-15 (Tue) | audiomoth | AM-EMU_ANCHOR_Fruit_Forest-05 | EMU_ANCHOR_Fruit_Forest | SFV-T0667 | 16.4564 | 77.9594 | No
1 | 2026-09-09 (Wed) | 2026-09-15 (Tue) | audiomoth | AM-EMU_ANCHOR_Wetland-01 | EMU_ANCHOR_Wetland | SFV-T0625 | 16.4598 | 77.9588 | No
1 | 2026-09-09 (Wed) | 2026-09-15 (Tue) | audiomoth | AM-EMU_ANCHOR_Wetland-02 | EMU_ANCHOR_Wetland | SFV-T0549 | 16.4596 | 77.9578 | No
1 | 2026-09-09 (Wed) | 2026-09-15 (Tue) | camera_trap | CAM-EMU_ANCHOR_Fruit_Forest-01 | EMU_ANCHOR_Fruit_Forest | SFV-T0461 | 16.4576 | 77.9564 | No
1 | 2026-09-09 (Wed) | 2026-09-15 (Tue) | camera_trap | CAM-EMU_ANCHOR_Wetland-01 | EMU_ANCHOR_Wetland | SFV-T0550 | 16.4598 | 77.9578 | No
2 | 2026-09-17 (Thur) | 2026-09-23 (Wed) | audiomoth | AM-SEG02-01 | SEG02 | SFV-T0109 | 16.4583 | 77.9522 | No
2 | 2026-09-17 (Thur) | 2026-09-23 (Wed) | audiomoth | AM-SEG02-02 | SEG02 | SFV-T0042 | 16.4592 | 77.9515 | No
2 | 2026-09-17 (Thur) | 2026-09-23 (Wed) | audiomoth | AM-SEG02-03 | SEG02 | SFV-T0138 | 16.4597 | 77.9525 | No
2 | 2026-09-17 (Thur) | 2026-09-23 (Wed) | audiomoth | AM-SEG02-04 | SEG02 | SFV-T0274 | 16.4583 | 77.9536 | No
2 | 2026-09-17 (Thur) | 2026-09-23 (Wed) | audiomoth | AM-SEG02-05 | SEG02 | SFV-T0047 | 16.4603 | 77.9515 | No
2 | 2026-09-17 (Thur) | 2026-09-23 (Wed) | audiomoth | AM-SEG04-01 | SEG04 | SFV-T0226 | 16.4617 | 77.9532 | No
2 | 2026-09-17 (Thur) | 2026-09-23 (Wed) | audiomoth | AM-SEG04-02 | SEG04 | SFV-T0294 | 16.4628 | 77.9537 | No
2 | 2026-09-17 (Thur) | 2026-09-23 (Wed) | camera_trap | CAM-SEG02-01 | SEG02 | SFV-T0020 | 16.4597 | 77.9513 | No
2 | 2026-09-17 (Thur) | 2026-09-23 (Wed) | camera_trap | CAM-SEG04-01 | SEG04 | SFV-T0195 | 16.4612 | 77.953 | No
3 | 2026-09-25 (Fri) | 2026-10-01 (Thur) | audiomoth | AM-SEG01-01 | SEG01 | SFV-T0416 | 16.4583 | 77.9552 | No
3 | 2026-09-25 (Fri) | 2026-10-01 (Thur) | audiomoth | AM-SEG01-02 | SEG01 | SFV-T0337 | 16.4569 | 77.9541 | No
3 | 2026-09-25 (Fri) | 2026-10-01 (Thur) | audiomoth | AM-SEG01-03 | SEG01 | SFV-T0100 | 16.4563 | 77.9522 | No
3 | 2026-09-25 (Fri) | 2026-10-01 (Thur) | audiomoth | AM-SEG01-04 | SEG01 | SFV-T0447 | 16.4569 | 77.9562 | No
3 | 2026-09-25 (Fri) | 2026-10-01 (Thur) | audiomoth | AM-SEG01-05 | SEG01 | SFV-T0297 | 16.4553 | 77.9538 | No
3 | 2026-09-25 (Fri) | 2026-10-01 (Thur) | audiomoth | AM-SEG01-06 | SEG01 | SFV-T0492 | 16.4587 | 77.9569 | No
3 | 2026-09-25 (Fri) | 2026-10-01 (Thur) | audiomoth | AM-EMU_ANCHOR_Rock_Guild-01 | EMU_ANCHOR_Rock_Guild | SFV-T0571 | 16.4562 | 77.9583 | No
3 | 2026-09-25 (Fri) | 2026-10-01 (Thur) | camera_trap | CAM-SEG01-01 | SEG01 | SFV-T0032 | 16.457 | 77.9515 | No
3 | 2026-09-25 (Fri) | 2026-10-01 (Thur) | camera_trap | CAM-SEG01-02 | SEG01 | SFV-T0422 | 16.4574 | 77.9555 | No
4 | 2026-10-03 (Sat) | 2026-10-09 (Fri) | audiomoth | AM-SEG03-01 | SEG03 | SFV-T0248 | 16.4596 | 77.9534 | No
4 | 2026-10-03 (Sat) | 2026-10-09 (Fri) | audiomoth | AM-SEG03-02 | SEG03 | SFV-T0353 | 16.461 | 77.9541 | No
4 | 2026-10-03 (Sat) | 2026-10-09 (Fri) | audiomoth | AM-SEG03-03 | SEG03 | SFV-T0345 | 16.4587 | 77.9541 | No
4 | 2026-10-03 (Sat) | 2026-10-09 (Fri) | audiomoth | AM-SEG03-04 | SEG03 | SFV-T0221 | 16.4605 | 77.9532 | No
4 | 2026-10-03 (Sat) | 2026-10-09 (Fri) | audiomoth | AM-SEG03-05 | SEG03 | SFV-T0213 | 16.4587 | 77.9531 | No
4 | 2026-10-03 (Sat) | 2026-10-09 (Fri) | camera_trap | CAM-SEG03-01 | SEG03 | SFV-T0164 | 16.4601 | 77.9527 | No
4 | 2026-10-03 (Sat) | 2026-10-09 (Fri) | camera_trap | CAM-SEG03-02 | SEG03 | SFV-T0282 | 16.4601 | 77.9536 | No